## Testing
Functional Area | Responsible | TC Number | Test Condition (TC) | Dev | System | User | Steps | Expected Results | Actual Results | Completion Status | Comments
ARGUS | Sharon/Prashant | AR001 | Assign Budget Department (B0780) to DoA's profile for CO access | √ |  |  | Modify User |  |  | Not Started
ARGUS | Sharon/Prashant | AR002 | Assign Budget Department (B0780) to prakash.prashant for CO access | √ |  |  | Modify User |  |  | Not Started
Not Started
Not Started
Grants | PSU/KL | GM001 | Establish XNODE/XPRGM(s) for UNU-IRADDA | √ |  |  | Create Project Node/Programme for UNU Programme Tree
Grants | PSU/KL | GM002 | Update Tree UNU_PROGRAMME
Grants | PSU/KL | GM003 | Establish Proposals | √ |  |  | Maintain Proposal > Submit Proposal > Generate Award |  |  | Not Started
Grants | PSU/KL | GM004 | Establish Awards and Projects | √ |  |  | Award Profile > Project > Project Activity > Project Budgets
Grants | PSU/KL | GM005 | Establish Project Budgets (Should only be done once KK Level 1 Budgets have been posted) | √ |  |  | Finalize Project Budgets (Biennium)
KK | Sharon | KK001 | Post Level 1 Budget | √ |  |  | Enter Budget Journals |  |  | Not Started
KK | Sharon | KK002 |  | √ | [5 empty] | Not Started
KK | Sharon | KK003 | Review Budget Activities | √ |  |  | Budget Details |  |  | Not Started
|  |  |  | √ | [5 empty] | Not Started
P Contracts | HR | PC001 | Create Personnel Contract(s) | √ |  |  | Add PSA/CTC/CIC/ICA |  |  | Not Started
P Contracts | HR | PC002 | Finalize/Approve and Stage Personnel Contract(s) | √ |  |  | Contract for Services |  |  | Not Started
P Contracts | HR | PC003 | Print Contract(s) | √ |  |  | Print Contract (UNU)
Purchasing | Angela | PO001 | Create Travel Request(s) | √ |  |  | Add/Update Requisitions
Purchasing | Angela | PO002 | Create quantity-based Requisition for asset and amount-based for services | √ |  |  | Add/Update Requisitions
Purchasing | Prashant | PO003 | Source Procurement Contracts/requisitions to PO | √ |  |  | Create PO |  |  | Not Started
Purchasing | Angela | PO004 | Verify Requisition approvals for Budget Department B0780 | √ |  |  | Send requisition for approvals to prakash@unu.edu
Purchasing | Angela | PO005 | Verify PO approvals for new PO BU by existing AOs | √ |  |  | Send PO for approvals to AOs |  |  | Not Started
Receipts | Angela | RT001 | Create Receipts (Non-Cap Profile) | √ |  |  | Add/Update Receipts
Receipts | Angela | RT002 | Interface Receipts to Asset Management | √
Receipts | Angela | RT003 |  | √
Assets | Huey Miin | AM001 | Create Assets using acquisition details for new Business Unit | √ |  |  | Basic Add
Assets | Huey Miin | AM002 | Verify Assets created from Receipts | √ |  |  | Interfaced Assets
Assets | Huey Miin | AM003 | Transfer Asset from existing OU to new OU | √ |  |  | AM transactions
Contracts | Way Peng |  | Create customer contract for donor agreements from 623 UU | √ |  |  | Regular Entry |  |  | Not Started
Contracts | Way Peng |  | Create milestones, revenue & billing plan | √ |  |  | Regular Entry
Contracts | Way Peng |  | Activate contract and set milstone to complete | √ |  |  | Regular Entry |  |  | Not Started
Contracts | Jack |  | Interface to BI/AR and GL | √ |  |  | Manual Run
AR | Way Peng |  | create pending item for OU 623UU in 600UU | √ |  |  | Regular Entry |  |  | Not Started
AR | Way Peng |  | record deposit for OU 623 UU in 600UU | √ |  |  | Regular Entry
AR | Way Peng |  | review if KK is updated | √ |  |  | Budget Details
|  |  |  | √ | [5 empty] | Not Started
Payables | Huey Miin | PY001 | Create Voucher from PO-Receipt(s) (3-way match) | √ |  |  | Regular Entry |  |  | Not Started
Payables | Huey Miin | PY002 | Create Voucher from PO (2-way match) | √ |  |  | Regular Entry
Payables | Prashant/ Huey Miin | PY003 | Match/Approve/Post Voucher(s) | √ |  |  | Online and Manual Run |  |  | Not Started
Payables | Huey Miin | PY004 | Run Paycycle to process 623UU AP BU voucher | √ |  |  | Online
Payables | Prashant/ Huey Miin | PY005 | Post Accruals/Payments to GL | √ |  |  | Manual Run |  |  | Not Started
GL | Sharon | GL001 | Create online journals for IRADDA specific ChartField combination | √ |  |  | Online |  |  | Not Started
GL | Sharon | GL002 | Generate TB and view numbers by Op Unit | √ |  |  | PSQuery/Reports
Not Started
* Transactions should be created for ChartFields belonging to IRADDA ** Fund Codes used should cover > Core Operating > Non-Core No Donor > Non-Core Program Dev > SPC
Operating Unit - 623 Budget Department - B0780 Expenditure Department - 78001