## Testing
Functional Area | Responsible | TC Number | Test Condition (TC) | Dev | System | User | Steps | Expected Results | Actual Results | Completion Status | Comments
ARGUS | Sharon/Prashant | AG001 | Assign Budget Department (B0780) to DoA's profile for CO access | √ |  |  | Modify User |  |  | Not Started
ARGUS | Sharon/Prashant | AG002 | Assign Budget Department (B0780) to prakash.prashant for CO access | √ |  |  | Modify User |  |  | Not Started
Grants | PSU/KL | GM001 | Establish XNODE/XPRGM(s) for UNU-IRADDA | √ |  |  | Create Project Node/Programme for UNU Programme Tree |  |  | Not Started
Grants | PSU/KL | GM002 | Update Tree UNU_PROGRAMME |  |  |  | Tree Manager - UNU_PROGRAMME/01/01/2010 |  |  | Not Started
Grants | PSU/KL | GM003 | Establish Proposals | √ |  |  | Maintain Proposal > Submit Proposal > Generate Award |  |  | Not Started
Grants | PSU/KL | GM004 | Establish Awards and Projects | √ |  |  | Award Profile > Project > Project Activity > Project Budgets |  |  | Not Started
Grants | PSU/KL | GM005 | Establish Project Budgets (Should only be done once KK Level 1 Budgets have been posted) | √ |  |  | Finalize Project Budgets (Biennium) |  |  | Not Started
KK | Sharon | KK001 | Post Level 1 Budget | √ |  |  | Enter Budget Journals |  |  | Not Started
KK | Way Peng | KK002 | Create/Review KK associations | √ |  |  | Manual KK Association |  |  | Not Started
KK | Sharon | KK003 | Review Budget Activities | √ |  |  | Budget Details |  |  | Not Started
√
P Contracts | HR | PC001 | Create Personnel Contract(s) | √ |  |  | Add PSA/CTC/CIC/ICA |  |  | Not Started
P Contracts | HR | PC002 | Finalize/Approve and Stage Personnel Contract(s) | √ |  |  | Contract for Services |  |  | Not Started
P Contracts | HR | PC003 | Print Contract(s) | √ |  |  | Print Contract (UNU) |  |  | Not Started
Purchasing | Angela | PO001 | Create Travel Request(s) | √ |  |  | Add/Update Requisitions |  |  | Not Started
Purchasing | Angela | PO002 | Create quantity-based Requisition for asset and amount-based for services | √ |  |  | Add/Update Requisitions |  |  | Not Started
Purchasing | Prashant | PO003 | Source Procurement Contracts/requisitions to PO | √ |  |  | Create PO |  |  | Not Started
Purchasing | Angela | PO004 | Verify Requisition approvals for Budget Department B0780 | √ |  |  | Send requisition for approvals to prakash@unu.edu |  |  | Not Started
Purchasing | Angela | PO005 | Verify PO approvals for new PO BU by existing AOs | √ |  |  | Send PO for approvals to AOs |  |  | Not Started
Receipts | Angela | RC001 | Create Receipts (Non-Cap Profile) | √ |  |  | Add/Update Receipts |  |  | Not Started
Receipts | Angela | RC002 | Interface Receipts to Asset Management | √ |  |  | Manual Run |  |  | Not Started
Receipts | Prashant | RC003 | Accrue Receipts | √ |  |  | Run Receipt Accrual and PORC700 |  |  | Not Started
Assets | Huey Miin | AM001 | Create Assets using acquisition details for new Business Unit | √ |  |  | Basic Add |  |  | Not Started
Assets | Huey Miin | AM002 | Verify Assets created from Receipts | √ |  |  | Interfaced Assets |  |  | Not Started
Assets | Huey Miin | AM003 | Transfer Asset from existing OU to new OU | √ |  |  | AM Transactions |  |  | Not Started
Contracts | Way Peng | CA001 | Create customer contract(s) for donor agreements for OU 623 UU | √ |  |  | Regular Entry |  |  | Not Started
Contracts | Way Peng | CA002 | Create milestones, revenue & billing plan | √ |  |  | Regular Entry |  |  | Not Started
Contracts | Way Peng | CA003 | Activate contract and set milestone to complete | √ |  |  | Regular Entry |  |  | Not Started
Contracts | Jack | CA004 | Interface to BI/AR and GL | √ |  |  | Manual Run |  |  | Not Started
AR | Way Peng | AR001 | Create pending item(s) for OU 623UU in 600UU | √ |  |  | Regular Entry |  |  | Not Started
AR | Way Peng | AR002 | Record deposit(s) for OU 623 UU in 600UU | √ |  |  | Regular Entry |  |  | Not Started
AR | Way Peng | AR003 | Review if KK is updated | √ |  |  | Budget Details |  |  | Not Started
Payables | Huey Miin | AP001 | Create Voucher(s) from PO/Receipt(s) | √ |  |  | Regular Entry |  |  | Not Started
Payables | Huey Miin | AP002 | Create Voucher(s) from PO | √ |  |  | Regular Entry |  |  | Not Started
Payables | Huey Miin | AP003 | Match/Approve Voucher(s) | √ |  |  | Online |  |  | Not Started
Payables | Huey Miin | AP004 | Run Paycycle to process 623UU AP BU voucher(s) | √ |  |  | Online |  |  | Not Started
Payables | Prashant | AP005 | Post Accruals/Payments to GL | √ |  |  | Manual Run |  |  | Not Started
GL | Sharon | GL001 | Create online journals for IRADDA specific CoA combination | √ |  |  | Online |  |  | Not Started
GL | Sharon | GL002 | Generate TB and view numbers by Op Unit | √ |  |  | PSQuery/Reports |  |  | Not Started
* Transactions should be created for ChartFields belonging to IRADDA ** Fund Codes used should cover > Core Operating > Non-Core No Donor > Non-Core Program Dev > SPC
Operating Unit - 623 Budget Department - B0780 Expenditure Department - 78001