## CutOver
Checkpoint # | Description | T1 | S1 | Cutover | Responsible Team | Duration (hh:mm) | Planned Start Date / Time (GMT +0800) | Planned End Date / Time (GMT +0800) | Completion Status | Comments
CP001 | Attach all DMS/SQL/DAT/SQL files to CR001451 | √ | √ | √ | UNU | 0:10 | 2014-07-03 17:00 | 2014-07-03 17:10 | Not Started
CP002 | Migrate and Build PeopleTools Project | √ | √ | √ | UNICC | 0:10 | 2013-08-02 08:10 | 2013-08-02 08:20 | Not Started
CP003 | > Export TGT for BACKUP > Import Config in P1 (DMS/DAT) | √ | √ | √ | UNICC | 0:15 | 2013-08-02 08:20 | 2013-08-02 08:35 | Not Started
CP004 | > Create new Permission List in P1 - 623UU > Update UNU setup in ARGUS for new Budget Department B0780 | √ | √ | √ | OIST/Atlas Security Team | 0:05 | 2013-08-02 08:35 | 2013-08-02 08:40 | Not Started
CP005 | > Setup BU security for 623UU (SQL) > Share Migration Logs with UNU | √ | √ | √ | UNICC | 0:30 | 2013-08-02 08:40 | 2013-08-02 09:10 | Not Started
CP006 | > Run Verification SQL in P1 > Ensure that the document numbers for PO/AP BU all start from ZERO | √ | √ | √ | UNU/Prashant | 0:30 | 2013-08-02 09:10 | 2013-08-02 09:40 | Not Started
CP007 | > UNU Finance to create new Operating Unit - 623 > **UNU Finance to check the Budget/Expenditure Department setup for UNU-IRADDA (B0780/78001) > Make sure B0780 has been setup as Budgetary Only | √ | √ | √ | UNU/Sharon | 0:30 | 2013-08-02 09:40 | 2013-08-02 10:10 | Not Started
CP008 | Modify KK/GL Trees for UNU > Add B0780 to KK Tree CC_UNUNI_DEPT > Add B0780 to GL Tree DEPT_ROLLUP_UNUNI | √ | √ | √ | UNU/Sharon/Prashant | 0:30 | 2013-08-02 10:10 | 2013-08-02 10:40 | Not Started
CP009 | Run Combo Build in P1 > Run Control ID - prakash.prashant/k UNU will trigger for Business Unit UNUNI and Ledger Group ACTUALS | √ | √ | √ | UNU/Prashant | 0:20 | 2013-08-02 10:40 | 2013-08-02 11:00 | Not Started
CP010 | Grants Setup > Create XNODE/XPRGM(s) for UNU-IRADDA > Update UNU Programme Tree -UNU_PROGRAMME/01/01/2010 > Inform PSU/Insititute to initiate Award Lifecycle | √ | √ | √ | UNU/Sharon | 1:00 | 2013-08-02 11:00 | 2013-08-02 12:00 | Not Started
CP011 | UPDATE/ADD Open Periods for new AP BU 623UU | √ | √ | √ | UNU/Sharon | 0:30 | 2013-08-02 12:00 | 2013-08-02 12:30 | Not Started
CP012 | UNU AP Paycycle Setup for new AP BU 623UU | √ | √ | √ | UNU/Sharon
CP013 | AP Voucher Bank Defaults | √ | √ | √ | UNU/AP Team | 1:00 | 2013-08-02 12:30 | 2013-08-02 13:30 | Not Started
** - UNU Finance to request SAS for creation of new Budget/Expenditure Department(s) for UNU-IRADDA. They should be B0780/78001 respectively